## Sizing function points
Scope | Class | Type | Select scope of project in the cell below | Select class of project in the cell below | Select type of project in the cell below
1 Subroutine | 1 Individual software | 1 Nonprocedural | 9 New system | 4 Single location—internal | 8 Client/server | Dropdown
2 Module | 2 Shareware | 2 Web applet | 9 | 4 | 8 | Values based category
3 Reusable module | 3 Academic software | 3 Batch
4 Disposable prototype | 4 Single location—internal | 4 Interactive | Total function points in the sowftware | 1280.0158
5 Evolutionary prototype | 5 Multilocation—internal | 5 Interactive GUI or web-based
6 Standalone program | 6 Contract project—civilian | 6 Batch database
7 Component of system | 7 Time sharing | 7 Interactive database
8 Release of system | 8 Military services | 8 Client/server
9 New system | 9 Internet | 9 Mathematical
10 Compound system | 10 Leased software | 10 Systems
| 11 Bundled software | 11 Communications
| 12 Marketed commercially | 12 Process control
| 13 Outsource contract | 13 Trusted system
| 14 Government contract | 14 Embedded
| 15 Military contract | 15 Image processing
16 Multimedia
17 Robotics
18 Artificial intelligence
19 Neural net
20 Hybrid: mixed

## Activity based cost analysis
Table 1 | Assumptions
| Work hours per month | 160 | <-add value
| Unpaid overtime per month | 0
| Average monthly salary in EUR | 4000 | <-add value
| Burden rate (%) | 60 | <-add value
| Burdened monthly rate in EUR | 6400
| Burdened hourly rate in EUR | 40
Table 2 | Activities | Staff FP Assignment | Monthly FP Production | Work Hours per FP | Burdened Cost per FP in EUR | Staffing per 1000 FP | Is the activity part of development process (Yes/No)?
| 01 Requirements | 250 | 175 | 0.91429 | 36.5714 | 4 | Yes | <-select dropdown
| 02 Prototyping | 350 | 150 | 1.0667 | 42.6667 | 2.8571 | Yes
| 03 Architecture | 2000 | 300 | 0.53333 | 21.3333 | 0.5 | Yes
| 04 Project plans | 1000 | 500 | 0.32 | 12.8 | 1 | No
| 05 Initial design | 250 | 175 | 0.91429 | 36.5714 | 4 | Yes
| 06 Detail design | 250 | 150 | 1.0667 | 42.6667 | 4 | Yes
| 07 Design reviews | 200 | 225 | 0.71111 | 28.4444 | 5 | Yes
| 08 Coding | 150 | 50 | 3.2 | 128 | 6.6667 | Yes
| 09 Reuse acquisition | 250 | 600 | 0.26667 | 10.6667 | 4 | Yes
| 10 Package purchase | 5000 | 400 | 0.4 | 16 | 0.2 | Yes
| 11 Code inspections | 150 | 150 | 1.0667 | 42.6667 | 6.6667 | No
| 12 Independent verification and validation | 2000 | 125 | 1.28 | 51.2 | 0.5 | No
| 13 Configuration management | 1000 | 1750 | 0.091429 | 3.6571 | 1 | Yes
| 14 Integration | 2000 | 250 | 0.64 | 25.6 | 0.5 | Yes
| 15 User documentation | 750 | 70 | 2.2857 | 91.4286 | 1.3333 | Yes
| 16 Unit testing | 150 | 150 | 1.0667 | 42.6667 | 6.6667 | Yes
| 17 Function testing | 350 | 150 | 1.0667 | 36.5714 | 2.8571 | Yes
| 18 Integration testing | 700 | 175 | 0.91429 | 36.5714 | 1.4286 | Yes
| 19 System testing | 2500 | 200 | 0.8 | 32 | 0.4 | No
| 20 Field (beta) testing | 1500 | 225 | 0.71111 | 28.4444 | 0.66667 | Yes
| 21 Acceptance testing | 750 | 350 | 0.45714 | 18.2857 | 1.3333 | Yes
| 22 Independent testing | 2500 | 200 | 0.8 | 32 | 0.4 | No
| 23 Quality assurance | 2000 | 150 | 1.0667 | 42.6667 | 0.5 | Yes
| 24 Installation and training | 5000 | 350 | 0.45714 | 18.2857 | 0.2 | Yes
| 25 Project management | 750 | 100 | 1.6 | 64 | 1.3333 | Yes
| Total |  |  | 19.4298 | 771.0984 | 49.0429 | <- updated automatically based on drowpdown above
Table 3 | Calculating total cost to develop software project | Fit to budget | Triangular | Jones' FP estimation
| Total number of function points in the project: | 472 | 753.02 | 1280.01
| Total work hours required to complete project (FP*Work hrs per FP) | 9170.8851 | 14631.0591 | 24870.3911
| Total cost for the project in EUR (FPs*Burden cost per FP) | 363958.4508 | 580652.5267 | 987013.6792

## Tender breakdown & FP Estimate
Epic | User Story | Work Items | External Inputs (EI) | External Outputs (EO) | External Inquiries (EQ) | Internal Logical Files (ILF) | External Interface Files (EIF) | Function Points Breakdown
[8 empty] | Minimum Estimate (FP) | Most Likely (FP) | Maximum Estimate (FP) | Weighted Average Estimate (FP)
Core Functionality | Data Registration and Processing | Real-time data registration (violations, warnings, arrests) | Login information, Incident type, Incident details, Additional notes, Attachments | Confirmation message, Backend data stored, Generated reports | Incident search, Validation queries, User history | User profiles, Incident records, Audit logs, Attachment files | Backend database, Law enforcement systems, Authentication systems, Mobile integration | 18 | 26 | 37 | 26.5
|  | Data processing and synchronization | User input data, device state information, error/conflict reports | Real-time data updates, error notifications, audit logs, user notifications | Data status queries, conflict resolution queries, audit trail inquiries, device connectivity status | User data files, synchronization logs, configuration files, error logs | Database interface, API interfaces, user authentication interfaces, reporting interfaces | 13 | 23 | 38 | 23.84
|  | Data inputs from mobile and desktop | User authentication inputs, Data entry inputs, Offline inputs | Confirmation messages, Error messages, Data sync status, UI updates | Data retrieval, Status Inquiries, Error Inquiries | User data files, Incident data files, offline data queues | DB interface, Synchronization Interface, UI adaptation, Notification Services | 15 | 23 | 32 | 23.83
|  | Data confirmation upon registration | User submits data through a form, submission event | Confirmation message, unique case number, log of recent entries | Inquiry about submission status, request to view log, retrieve details with case number | Logical file for submitted entries, log file for submissions, user profiles | Integration with a backend database, reporting tools, notification systems | 9 | 15 | 23 | 15.5
| Legality and Compliance with Policy Changes | Workflow configuration for law and policy updates | admin credentials, workflow configurations, legal/policy changes, versioning inputs, audit/compliance notes, low-code/no-code inputs for workflow logic | Confirmation messages, notifications of workflow changes, audit logs, version history reports, dashboards summarizing workflows and changes | View current workflows, review workflow history, pending workflow updates, audit logs of modifications, check for errors or conflicts in workflows | Workflow definitions, version control file, audit log file, user profiles, legal/policy references related to workflows | Authentication interface, audit interface, notification interface, integration with external policy systems, reporting interface for workflow changes | 22 | 30 | 44 | 31
|  | Update alerts for legal changes | Legal or policy data from external sources (legal databases or APIs), admin credentials | Alerts or notifications for system administrators, detailed information on workflow impacts | Inquiries to retrieve recent legal updates, workflow impact inquiries, alert status inquiries | Legal update logs, workflow modification logs, notification records, admin action logs | Legal system APIs, notification system interfaces, audit and logging systems | 33 | 40 | 48 | 40.17
|  | Audit records for updates made to the system | User actions, Changes to legal policies and workflow, User roles | Audit logs, Exported reports of audit logs, Alerts for pending or approved changes | Search queries for audit logs, Review or approval status of workflows | Audit trail data, Workflow change history files, User roles and permissions, Legal workflow configuration logs | External logging systems, Interfaces for administrators to search and export logs, Notification or alert system interfaces | 22 | 30 | 44 | 31
System Integration | Data Integration with Other Systems | Data interaction capabilities between systems | Data exchange requests, configuration settings, user credentials, error logs | Confirmation messages, data logs, error reports, data packets | Status inquiries, logs of data exchanges, error inquiries, configuration inquiries | Configuration files, log files, mapping files, user authentication files | APIs, file transfer interfaces, webhooks, dashboard interfaces | 10 | 15 | 25 | 16.87
|  | Real-time synchronization | Data change events, user input, configuration settings, error reports | Success notifications, conflict resolution messages, error logs, summary reports | Status inquiries, conflict queries, historical logs, configuration queries | Data change logs, error logs, user configuration files, synchronization history files | API interfaces, file transfer protocols, event-driven interfaces, monitoring dashboards | 15 | 25 | 34 | 24.83
|  | System alerts for data exchange failures or conflicts | Error reports, user configuration settings, data synchronization logs, action triggers | Alert notifications, detailed error reports, recommended actions, retry logs | Status checks, alert history, configuration queries, error resolution | Synchronization logs, user preferences files, error code repository, alert history files | Monitoring dashboard, email/SMS notification services, API interfaces, logging tools | 10 | 18 | 27 | 18.17
| Interaction with Existing Systems | Parallel operation with the old system | User credentials, system toggle, data updates, real-time system activity logs | Notifications, system performance reports, data synchronization statuses | System status checks, error logs, inquiry into active sessions | Session logs, transition logs, performance metrics, data sync logs, user access logs | Interfaces with data sync services, logging systems, external system monitoring tools, old system APIs | 20 | 28 | 36 | 28
|  | Updates for handling old/new cases | User actions/filters, Case data entry, System configuration inputs, Status updates for unresolved cases | Flagged cases, Filtered case lists based on system origin or status, Case status updates, User notifications, Audit logs | Filter-based inquiries, Case status inquiries, Case transition inquiries, System-handling insights | Case data files, System flag files, Status logs, Filter configuration files, Audit and history files | System switching API, Case management systems, Notification systems, Reporting and analytics tools, User authentication systems | 25 | 36 | 53 | 38
|  | Data accessibility from both old and new systems | User queries, User actions, Authentication/authorization inputs, Data integrity checks | Unified data display, User notifications/alerts, Data consistency messages, Audit and log entries, Search results | Data queries, Data source identification, Edit permissions inquiries, Data integrity inquiries | Unified data views, Search query logs, Data consistency logs, Edit logs and audit trails, Permission and configuration files | Data query interfaces, Data display interfaces, Notification systems, Data integrity validation interfaces, Audit and monitoring systems | 23 | 32 | 45 | 32
Mobile and Desktop Usability | Mobile and Desktop Usability | Responsive UI for mobile and desktop | User inputs, device detection, touch inputs, dynamic form fields | Responsive layouts, confirmation messages, data displays, error messages | Data retrieval, device status, navigation queries, user support inquiries | User profiles, input forms, error logs, configuration files | APIs for data exchange, user authentication services, analytics tools, CMS interfaces | 14 | 24 | 34 | 24.66
|  | Consistent user experience across different devices | User credentials, enforcement data, device-specific inputs, settings/preferences | Confirmation messages, real-time updates, sync status notifications, UI updates | Data retrieval, sync status inquiry, feature access, error reporting | User profiles, data entries, activity logs, error logs | Authentication interfaces, data sync interfaces, logging interfaces, user notification interfaces | 14 | 24 | 34 | 24
|  | Offline data entry | User data entry, sync triggers, authentication and authorization inputs | data syncronization, sync status notifications, offline data confirmation | sync status inquiries, offline data availability, manual sync requests | offline data cache, sync logs, user session data, data queue files | Network status monitoring, data sync APIs, notification services, data integrity check interface, error reporting interfaces | 21 | 31 | 43 | 31
Security and Compliance | User Management and Access Control | Access control for different roles | Role definitions, permissions configuration, user details, role modifications | confirmation messages, access control logs, error messages, reports | Role permissions, user access level, change requests, audit queries | role definitions file, premissions file, access logs file, user role assignments file | user management systems, reporting tools, external APIs, configuration management interfaces | 14 | 21 | 29 | 21.16
|  | Permissions management for different roles | Role assignments, permission changes, user information | confirmation messages, audit logs, error messages | role information queries, user role status, audit trail access | user roles file, permissions file, audit log file, user information file | user management system integration, reporting tools, access control systems, APIs | 10 | 20 | 28 | 20.66
|  | Security logs for access attempts and changes | input description, high complexity | output description, medium complexity | Inquiry description, medium complexity | Logical file description, medium complexity | Interface description, medium complexity | 15 | 25 | 35 | 25
| Compliance with GDPR and Data Privacy | Data encryption for sensitive information | data to be encrypted, encryption settings, user credentials | encrypted data, confirmation messages, audit logs | encryption status inquiry, audit logs requests, encryption configuration inquiry | user profiles, encryption keys, audit logs | DB interface, external system interface, Key management interface | 5 | 8 | 12 | 8.17
|  | Data deletion and privacy for GDPR compliance | user requests, user creds, data identifiers, compliance documentation | confirmation messages, audit logs, status update, error messages | request status, audit log access, compliance queries | user request logs, audit trails, user profiles, compliance records | authentication interfaces, compliance management interfaces, data management interfaces, reporting interfaces | 25 | 39 | 62 | 40.5
|  | Security audit using data access logs | User creds, access requests, modification details, timestamp, action type | audit logs, exported log files, confirmation messages, compliance reports | log retrieval, log export status, access requests, compliance queries | access logs, modification logs, user profiles, audit trails, retention policies | logging interfaces, audit interfaces, user management interfaces, compliance management interfaces, notification interface | 5 | 8 | 12 | 8.17
Analytics and Reporting | Analytics and Reporting | Report generation based on enforcement data | Users enter parameters (time period, incident type, officer name) to generate reports. | The system generates reports in multiple formats (summary, detailed) with export options (PDF, Excel, CSV). | Users can query past reports based on filters (time, incident type, officer name). | System stores data on enforcement activities, report configurations, and generated report metadata. | Data exchanges with external systems like case management or analytics tools in multiple formats (XML, JSON). | 21 | 31 | 41 | 31
|  | Export reports in various formats | Users select report parameters (PDF, Excel, CSV) and request export | The system generates and exports reports in selected formats, maintaining original formatting (PDF, Excel, CSV) | Users can inquire about previous report exports or check the status of export requests. | The system stores metadata for exported reports (e.g., file type, export date, recipient). | Exported reports can be shared with other systems (e.g., emailed reports, shared to external services like cloud storage). | 18 | 27 | 36 | 27
|  | Filters for specific data (time periods, incident types, etc) | Users select filters (eg. time period, incident type, officer, location) for report generation | The system generates reports based on the selected filters, displaying filtered data | Users can inquire about reports that have been generated based on specific filters or check which filters were applied | The system stores user-defined filter preferences and report metadata for generating recurring reports | The filtering function interacts with the report generation and data systems to pull filtered information | 15 | 23 | 31 | 23
Inter-Municipal Collaboration | Collaboration with other Municipalities | Setup for tenant agreeements with multiple municipalities under one contract | Municipality onboarding, user credentials, enforcement data, permissions management | Data segmentation, user-specific reports, notifications, municipality-specific records | Municipality-specific data retrieval, onboarding status inquiries, permission checks | Municipality data files, user roles and permissions, enforcement data, system logs | External municipal system integrations, data exchange, permission management interfaces | 18 | 27 | 36 | 27
|  | Data segregation for different municipalities | Municipality configurations, user credentials, enforcement data, data-sharing permissions | Confirmation of data segregation, municipality-specific reports, notifications on data access | Data retrieval by municipality, segregation checks, access control inquiries | Municipality-specific data files, permission records, workflows, access logs | Data segregation logic, external system interfaces for shared data, authentication interfaces | 17 | 24 | 34 | 24.5
|  | Shared system with various municipality configurations | Configuration settings, user creds, preference selections, data entry | confirmation messages, customized workflows, audit logs, reports | configuration status, workflow access, customization history, error reporting | municipality profiles, configuration logs, user profiles, workflow definitions | Admin interfaces, data exchange interfaces, reporting interfaces, user authentication interfaces | 13 | 24 | 35 | 24.66
Training and User Feedback | User Training and Support | Training materials for both mobile and desktop users | User feedback, training content, usage analytics, device type | training materials, usage reports, completion certificates, feedback confirmation | material availability, access issues, content suggestions, progress tracking | training material repo, user profiles, access logs, feedback logs | leraning management systems, content management systems, analytics tools, notification systems | 17 | 26 | 36 | 26.17
|  | Support system for user issues | User queries, user information, issue type, attachments, priority level | confirmation messages, ticket status update, response messages, support ticket summary, error notifications | check ticket status, retrieve previous tickets, update ticket info, search FAQs | Support tickets DB, user profiles, issue types list, response templates | user authentication interface, notification system interface, reporting interface, knowledge base interface | 5 | 8 | 12 | 8.33
|  | User feedback for improving training | User feedback entries, user information, feedback category selection, device information | confirmation messages, feedback status updates, reports for admins, categorization notifications | feedback submission status, categories of feedback, feedback trends | feedback logs, categorization files, feedback status records, user profiles | User management interface, reporting interface, email notification interface, feedback categorization interface | 5 | 8 | 12 | 8.33
[7 empty] | TOTAL | 487 | 739 | 1048 | 753.02
Possible cost cutting eliminations
Epic | User Story | Work Item | FP
Inter municipal collaboration |  |  | -75
|  | Training materials for both mobile and desktop users | -26.17
|  | Export reports in various formats | -27
|  | Offline data entry | -31
|  | Update alerts for legal changes | -40.17
|  | Audit records for updates made to the system | -31
|  | User feedback for improving training | -8.33
|  | Consistent user experience across different devices | -24
|  | System alerts for data exchange failures or conflicts (still fails but no alert will be raised) | -18.17
|  | TOTAL | -280.84 | ≈ 281 FP
|  | Total Weighted Average Estimated FPs | 753.02
|  | FPs of the tender after constraints | 472
|  | Final cost = FP * Burden cost per FP = | EUR 370000,05

## RoT Based on LOC
Size of LOC | Coding LOC/month | Coding Effort in months | Testing Effort in % | Non-code Effort in % | Total Effort in months | Net LOC/month
1 | 2500 | 0.0004 | 10 | 10 | 0.0005 | 2083 | Size of LOC | Coding Effort (months) | Testing Effort (%) | Non-code Effort (%) | Total Effort (months)
10 | 2250 | 0.0044 | 20 | 20 | 0.0062 | 1607 | 10000 | 6.6667 | 75 | 70 | 17
100 | 2000 | 0.05 | 40 | 40 | 0.09 | 1111 | 100000 | 83.3333 | 100 | 100 | 250
1000 | 1750 | 0.5714 | 50 | 50 | 1.2 | 833 | 1000000 | 1000 | 125 | 150 | 3750
10000 | 1500 | 6.6667 | 75 | 70 | 17 | 588
100000 | 1200 | 83.3333 | 100 | 100 | 250 | 400
1000000 | 1000 | 1000 | 125 | 150 | 3750 | 267
Activity | End-user projects | MIS projects | Systems projects | Commercial projects | Military projects |  | Activity | End-user | MIS | Military
Requirements definition | 0 | 7 | 8 | 4 | 10 |  | Requirements definition | 0 | 7 | 10
Design | 10 | 12 | 15 | 10 | 15 |  | Design | 10 | 12 | 15
Coding | 60 | 25 | 18 | 25 | 18 |  | Coding | 60 | 25 | 18
Testing | 30 | 30 | 30 | 36 | 22 |  | Testing | 30 | 30 | 22
Change management | 0 | 6 | 10 | 5 | 12 |  | Change management | 0 | 6 | 12
Documentation | 0 | 8 | 7 | 10 | 10 |  | Documentation | 0 | 8 | 10
Project management | 0 | 12 | 12 | 10 | 13 |  | Project management | 0 | 12 | 13
Total | 100 | 100 | 100 | 100 | 100 |  | Total % | 100 | 100 | 100
Size of LOC | Coding LOC/month | Coding Effort (months) | Testing Effort (%) | Non-code Effort (%) | Total Effort (months) | Net LOC/month
10000 | 1500 | 6.6667 | 75 | 70 | 17 | 588
100000 | 1200 | 83.3333 | 100 | 100 | 250 | 400
1000000 | 1000 | 1000 | 125 | 150 | 3750 | 267
Size of LOC | Coding LOC/month | Coding Effort (months) | Testing Effort (%) | Non-code Effort (%) | Total Effort (months) | Net LOC/month
100000 | 1200 | 83.3333 | 100 | 100 | 250 | 400